|  | Legend |  |  | ND = No data available Yellow = Highest Orange = Lowest |
| --- | --- | --- | --- | --- |
| Fidelity | - Are field officers facilitating promoter meetings twice a month as planned? | Number of lesson delivered by field officers | Promoter Register | Field Officer; Number of Lessons Delivered. Carolyne; 2. Douglas; 2. Bethsheba; 1. Ester; 2. Janet; 2. Peter; 2. Diana; 2. Davis; 1. Total; 14. Promoter; Total Absences; Attendance Rate. Samwel Obondi; 1; 93%. Mellen Mungei; 2; 86%. James Okari; 1; 93%. Winfridah Osebe; 0; 100%. Joash Abdallah; 1; 93%. |
| Fidelity | - Are promoters facilitating CGV meetings twice a month as planned? | Percent of lessons delivered to CGVS |  | 7 Month Promoter Home Visit Summary; Completed; Intended; %. (Dec 2018 - June 2019). Total number of group meetings held; 70; 70; 100%. Total number of group meetings per promoter; 14; 14; 100%. |
| Fidelity | - Are promoters completing home visits when CGVs do not attend the bi-weekly meetings? | Percent of homes visits completed for CGVs when not in attendance |  | There was no available electronic data to assess this indicator at the time of analysis. |
| Delivery | - Are promoters completing all the CGV home visits as intended? | Percent of home visits completed following each lesson |  | 7 Month Promoter Home Visit Summary (Dec 2018 - June 2019); Number of CGVs; Completed Home Visits; Intended Home Visits; %; Average Completed Across CGV. Promoter CG1; 10; 54; 140; 39%; 5.40. Promoter CG2; 7; 47; 98; 48%; 6.71. Promoter CG3; 8; 53; 112; 47%; 6.63. Promoter CG4; 9; 44; 126; 35%; 4.89. Promoter CG5; 9; 49; 126; 39%; 5.44. All promoters; 43; 247; 602; 41%; 5.74. |
|  |  | Percent of first and second lesson home visits completed |  | 7 Month Promoter Home Visit Summary (Dec 2018 - June 2019); Number of CGVs; Completed First Home Visits; Intended First Home Visits; %; Average Completed Across CGV. Promoter CG1; 10; 25; 70; 36%; 2.50. Promoter CG2; 7; 28; 49; 57%; 4.00. Promoter CG3; 8; 26; 56; 46%; 3.25. Promoter CG4; 9; 19; 63; 30%; 2.11. Promoter CG5; 9; 27; 63; 43%; 3.00. All promoters; 43; 125; 301; 42%; 2.91. |
|  |  | Percent of second lesson home visits completed |  | 7 Month Promoter Home Visit Summary (Dec 2018 - June 2019); Number of CGVs; Completed Second Home Visits; Intended Second Home Visits; %; Average Completed Across CGV. Promoter CG1; 10; 29; 70; 41%; 2.90. Promoter CG2; 7; 19; 49; 39%; 2.71. Promoter CG3; 8; 27; 56; 48%; 3.38. Promoter CG4; 9; 25; 63; 40%; 2.78. Promoter CG5; 9; 22; 63; 35%; 2.44. All promoters; 43; 122; 301; 41%; 2.84. |
|  |  | Number of home visits each CGV received from Dec 2018 – June 2019 |  | There was no available electronic data to assess this indicator at the time of analysis. |
| Delivery | - Are CGVs completing home visits when neighbor women do not attend the bi-weekly meetings? | Percent of homes visits completed by CGVs |  | There was no available electronic data to assess this indicator at the time of analysis. |
| Delivery | - Are CGVs completing home visits to all neighbor women after each lesson? | Percent of home visits completed after each meeting |  | 7 Month CGV Home Visits (Dec 2018 - June 2019); Number of CGVs; Number of Women; Completed Home Visits; Intended Home Visits; %; Average Completed Across CGV. CG1 - CGVs; 10; 118; 613; 1652; 37%; 5.19. CG2 - CGVs; 7; 73; 379; 1022; 37%; 5.19. CG3 - CGVs; 8; 82; 454; 1148; 40%; 5.54. CG4 - CGVs; 9; 88; 516; 1232; 42%; 5.86. CG5 - CGVs; 9; 100; 588; 1400; 42%; 5.88. All CG; 43; 461; 2550; 6454; 40%; 5.53. |
|  |  | Percent of first lesson home visits completed |  | 7 Month CGV Home Visits (Dec 2018 - June 2019); Number of CGVs; Number of Women; Completed First Home Visits; Intended First Home Visits; %; Average Completed Across CGV. CG1 - CGVs; 10; 118; 308; 826; 38%; 2.61. CG2 - CGVs; 7; 73; 185; 511; 39%; 2.53. CG3 - CGVs; 8; 82; 225; 574; 36%; 2.74. CG4 - CGVs; 9; 88; 243; 616; 36%; 2.76. CG5 - CGVs; 9; 100; 299; 700; 33%; 2.99. All CG; 43; 461; 1260; 3227; 37%; 2.73. |
|  |  | Percent of second lesson home visits completed |  | 7 Month CGV Home Visits (Dec 2018 - June 2019); Number of CGVs; Number of Women; Completed Second Home Visits; Intended Second Home Visits; %; Average Completed Across CGV. CG1 - CGVs; 10; 118; 305; 826; 37%; 2.58. CG2 - CGVs; 7; 73; 194; 511; 38%; 2.66. CG3 - CGVs; 8; 82; 229; 574; 40%; 2.79. CG4 - CGVs; 9; 88; 273; 616; 44%; 3.10. CG5 - CGVs; 9; 100; 289; 700; 41%; 2.89. All CG; 43; 461; 1290; 3227; 40%; 2.80. |
|  |  | Number of home visits each neighbor women received from her CGV from Dec 2018 – June 2019 |  | There was no available electronic data to assess this indicator at the time of analysis. |
| Fidelity | - Are promoters managing the appropriate number of CGVs? | Average number of CGVs assigned to each promoter |  | Number of CGVs. Promoter CG1; 10. Promoter CG2; 7. Promoter CG3; 8. Promoter CG4; 9. Promoter CG5; 9. All promoters; 43. |
| Reach | - Are promoters achieving at least 80% attendance at each CGV lesson? | Average attendance rate across all meetings held |  | 7 Month Promoter Meeting Attendance (Dec 2018 - June 2019); Number of CGVs; Attendance Rate All meetings; Intended Attendance rate; %. Promoter CG1; 10; 99; 140; 71%. Promoter CG2; 7; 75; 98; 77%. Promoter CG3; 8; 67; 112; 60%. Promoter CG4; 9; 84; 126; 67%. Promoter CG5; 9; 87; 126; 69%. All promoters; 43; 412; 602; 68%. |
|  |  | Number of meetings with 80% attendance |  | 7 Month Promoter Meeting Attendance (Dec 2018 - June 2019); Total Number of Meetings; Number of Meeting with 80% Attendance; %. Promoter CG1; 14; 4; 29%. Promoter CG2; 14; 4; 29%. Promoter CG3; 14; 1; 7%. Promoter CG4; 14; 2; 14%. Promoter CG5; 14; 1; 7%. All promoters; 70; 12; 17%. |
|  |  | Most common number of CGVs that attend care group meetings |  | 7 Month Promoter Meeting Attendance (Dec 2018 - June 2019); Average CGV Attendance per Meeting. Promoter CG1; 7.1. Promoter CG2; 5.4. Promoter CG3; 4.8. Promoter CG4; 6. Promoter CG5; 6.2. Average (All CGs); 5.9. |
| Reach | - Are CGVs achieving at least 80% attendance at each neighbor group meeting? | Average attendance rate across all meetings held |  | 7 Month CGV Home Visits (Dec 2018 - June 2019); Number of CGVs; Number of Women; Attendance Rate All meetings; Intended Attendance rate; %. CG1 - CGVs; 10; 118; 702; 1652; 42%. CG2 - CGVs; 7; 73; 627; 1022; 61%. CG3 - CGVs; 8; 82; 556; 1148; 48%. CG4 - CGVs; 9; 88; 582; 1232; 47%. CG5 - CGVs; 9; 100; 763; 1400; 55%. All CG; 43; 461; 3230; 6454; 50%. CG 1; Number of Women; Attendance Rate; Intended Attendance; %. CGV A; 13; 70; 182; 38%. CGV B; 12; 98; 168; 58%. CGV C; 14; 94; 196; 48%. CGV D; 14; 73; 196; 37%. CGV E; 11; 69; 154; 45%. CGV F; 10; 60; 140; 43%. CGV G; 11; 69; 154; 45%. CGV H; 9; 57; 126; 45%. CGV I; 12; 55; 168; 33%. CGV J; 12; 57; 168; 34%. CG2; Number of Women; Attendance Rate; Intended Attendance; %. CGV A; 12; 89; 168; 53%. CGV B; 11; 109; 154; 71%. CGV C; 9; 91; 126; 72%. CGV D; 14; 86; 196; 44%. CGV E; 8; 96; 112; 86%. CGV F; 10; 98; 140; 70%. CGV G; 9; 58; 126; 46%. CG3; Number of Women; Attendance Rate; Intended Attendance; %. CGV A; 13; 146; 182; 80%. CGV B; 13; 81; 182; 45%. CGV C; 8; 59; 112; 53%. CGV D; 8; 55; 112; 49%. CGV E; 11; 58; 154; 38%. CGV F; 10; 67; 140; 48%. CGV G; 9; 51; 126; 40%. CGV H; 10; 39; 140; 28%. CG4; Number of Women; Attendance Rate; Intended Attendance; %. CGV A; 12; 72; 168; 43%. CGV B; 11; 75; 154; 49%. CGV C; 9; 74; 126; 59%. CGV D; 8; 73; 112; 65%. CGV E; 9; 76; 126; 60%. CGV F; 8; 60; 112; 54%. CGV G; 10; 53; 140; 38%. CGV H; 10; 51; 140; 36%. CGV I; 11; 48; 154; 31%. CG5; Number of Women; Attendance Rate; Intended Attendance; %. CGV A; 9; 72; 126; 57%. CGV B; 11; 88; 154; 57%. CGV C; 9; 79; 126; 63%. CGV D; 15; 100; 210; 48%. CGV E; 15; 86; 210; 41%. CGV F; 11; 104; 154; 68%. CGV G; 11; 93; 154; 60%. CGV H; 9; 60; 126; 48%. CGV I; 10; 81; 140; 58%. |
|  |  | Percent of meetings meeting 80% attendance |  | 7 Month CGV Meeting Attendance (Dec 2018 - June 2019); Total Number of Meetings; Total Number of Meetings; %. CG1 - CGVs; 140; 1; 1%. CG2 - CGVs; 140; 13; 9%. CG3 - CGVs; 140; 7; 5%. CG4 - CGVs; 140; 1; 1%. CG5 - CGVs; 140; 3; 2%. |
| Fidelity | - Are promoters completing and submitting the care group registry forms every two weeks as planned? | Number of completed summary sheets collected |  | There is no available electronic data to assess this indicator at the time of analysis. |
| Fidelity | - Are field officers collecting vital events from promoters each month as planned? | Average QIVC score on group lesson checklist item #18 and #19 covering vital events |  | Average performance on group meeting items # 18, 19 (All Promoters); %. Q1; 63%. Q2; 90%. Q1 & Q2; 75%. Average performance on group meeting items # 18, 19; Promoter 1; Promoter 2; Promoter 3; Promoter 4; Promoter 5. Q1; 100%; 100%; 0%; 50%. Q2; 100%; 100%; 100%; 50%; 100%. Q1 & Q2; 100%; 100%; 50%; 50%; 75%. |
| Fidelity | - Are field officers completing quarterly QIVCs for each promoter? | Percent of completed promoter QIVCs |  | QIVC completion Rate – Promoter; %. Q1; 80%. Q2; 100%. Q1 & Q2; 90%. |
| Fidelity | - Are field officers completing quarterly feedback QIVCs for each promoter? | Percent of completed feedback QIVCs for promoter |  | QIVC completion Rate – Promoter Feedback; %. Q1; 60%. Q2; 100%. Q1 & Q2; 80%. |
| Delivery | - Are promoters exhibiting the facilitation skills at an acceptable standard of quality? | Average QIVC score on checklist items accessing facilitation skills across promoters |  | Average performance on facilitation skills – Promoters; %. Q1; 81%. Q2; 91%. Q1 & Q2; 87%. |
|  |  | Average QIVC score on checklist items accessing facilitation skills for each promoter |  | Average performance on facilitation skills; Promoter 1; Promoter 2; Promoter 3; Promoter 4; Promoter 5. Q1; 54%; 92%; 92%; ND; 85%. Q2; 77%; 100%; 100%; 92%; 85%. Q1 & Q2; 65%; 96%; 96%; 92%; 85%. |
| Delivery Delivery | - Are the promoters completing the most important activities during the CGV meetings including collection of vital events, recap of last lesson, commitment confirmation, lesson plan, and discussion of barriers? | Average QIVC score across promoters on check list items: 18, 19, 20, 21, 22, 23, 26, 27, 28 across promoters |  | Average performance on group meeting items # 18, 19, 20, 21, 22, 23, 26, 27, 28; %. Q1 average performance on facilitation skills; 81%. Q2 average performance on facilitation skills; 91%. Q1 & Q2 average performance on facilitation skills; 87%. |
|  |  | Average QIVC score across promoters on check list items: 18, 19, 20, 21, 22, 23, 26, 27, 28 for each promoter |  | Average performance on group meeting items # 18, 19, 20, 21, 22, 23, 26, 27, 28; Promoter 1; Promoter 2; Promoter 3; Promoter 4; Promoter 5. Q1; 67%; 78%; 67%; ND; 44%. Q2; 67%; 89%; 89%; 67%; 78%. Q1 & Q2; 67%; 83%; 78%; 67%; 61%. |
| Delivery | - Are promoters exhibiting mastery of the lesson material? Are promoters delivering educational content accurately and completely? | Average QIVC scores across all promoters for check list items #35, 36, and 37 |  | Average performance on group meeting items # 35, 36, 37; %. Q1; 100%. Q2; 100%. Q1 & Q2; 100%. |
|  |  | Average QIVC scores across all promoters for check list items #35, 36, and 37 |  | Average performance on group meeting items # 35, 36, 37; Promoter 1; Promoter 2; Promoter 3; Promoter 4; Promoter 5. Q1; 100%; 100%; 100%; No Data; 100%. Q2; 100%; 100%; 100%; 100%; 100%. Q1 & Q2; 100%; 100%; 100%; 100%; 100%. |
| Delivery | - Are promoters conducting quarterly QIVCs for each of their CGVs? Are promoters conducting QIVCs for CGV home visits? | Percent of QIVCs completed for CGVs |  | Home Visit QIVC Completion Rate - CGV; %. Q1; 21%. Q2; 80%. Q1 & Q2; 50%. Group Meeting QIVC completion Rate - CGV; %. Q1; 41%. Q2; 100%. Q1 & Q2; 71%. |
| Delivery | - Are CGVs exhibiting the facilitation skills at an acceptable standard of quality? | Average QIVC score on checklist items accessing facilitation skills across CGVs |  | Average performance on facilitation skills – All CGVs; %. Q1; 81%. Q2; 74%. Q1 & Q2; 77%. |
|  |  | Average QIVC score on checklist items accessing facilitation skills for each CGV |  | CG1 Average performance facilitation skills; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; CGV I; CGV J; Total. Q1; 92%; ND; 64%; ND; 79%; 69%; ND; 77%; 77%; ND; 73%. Q2; 77%; 73%; 77%; 73%; 73%; 77%; 85%; 69%; 77%; 88%; 77%. Q1 & Q2; 85%; 73%; 71%; 73%; 76%; 73%; 85%; 73%; 77%; 88%; 77%. CG2 Average performance facilitation skills; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; Total. Q1; 92%; 92%; 100%; ND; 92%; ND; ND; 94%. Q2; 77%; 65%; 81%; 77%; 81%; 62%; 77%; 74%. Q1 & Q2; 85%; 79%; 90%; 77%; 87%; 62%; 77%; 79%. CG3 Average performance facilitation skills; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; Total. Q1; 73%; 74%; ND; 77%; 62%; 85%; 62%; 77%; 73%. Q2; 78%; 78%; 81%; 74%; 85%; 70%; 78%; 79%; 78%. Q1 & Q2; 75%; 76%; 81%; 75%; 73%; 77%; 70%; 78%; 76%. CG4 Average performance facilitation skills; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; CGV I; Total. Q1; ND; ND; ND; ND; ND; ND; ND; ND; ND; ND. Q2; 64%; 76%; 68%; 68%; 60%; 92%; 72%; 84%; 80%; 74%. Q1 & Q2; 64%; 76%; 68%; 68%; 60%; 92%; 72%; 84%; 80%; 75%. CG5 Average performance facilitation skills; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; CGV I; Total. Q1; ND; 81%; ND; ND; 85%; ND; ND; ND; ND; 83%. Q2; 73%; 65%; 62%; 65%; 62%; 73%; 58%; 62%; 69%; 65%. Q1 & Q2; 73%; 73%; 62%; 65%; 73%; 73%; 58%; 62%; 69%; 67%. |
| Delivery | - Are the CGVs completing the most important aspects of the neighbor group meetings including collection of vital events, recap of last lesson, commitment confirmation, lesson plan, and discussion of barriers? | Average QIVC score across promoters on check list items: 18, 19, 20, 21, 22, 23, 26, 27, 28 across CGVs |  | Average performance on group meeting items # 18, 19, 20, 21, 22, 23, 26, 27, 28 – All CGVs; %. Q1; 58%. Q2; 59%. Q1 & Q2; 59%. |
|  |  | Average QIVC score across promoters on check list items: 18, 19, 20, 21, 22, 23, 26, 27, 28 for each CGVs |  | CG1 Average performance on group meeting items # 18, 19, 20, 21, 22, 23, 26, 27, 28; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; CGV I; CGV J; Total. Q1; 89%; ND; ND; ND; ND; 67%; ND; 67%; ND; ND; 67%. Q2; 33%; 33%; 33%; 56%; 44%; 44%; 67%; 67%; 44%; 56%; 49%. Q1 & Q2; 61%; 33%; 33%; 56%; 44%; 56%; 67%; 67%; 44%; 56%; 51%. CG2 Average performance on group meeting items # 18, 19, 20, 21, 22, 23, 26, 27, 28; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; Total. Q1; 89%; 89%; 78%; ND; 78%; ND; ND; 83%. Q2; 50%; 67%; 78%; 89%; 44%; 78%; 56%; 66%. Q1 & Q2; 69%; 78%; 78%; 89%; 61%; 78%; 56%; 73%. CG3 Average performance on group meeting items # 18, 19, 20, 21, 22, 23, 26, 27, 28; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; Total. Q1; 89%; 44%; ND; 67%; 33%; ND; 56%; 33%; 54%. Q2; 78%; 56%; 67%; 88%; 56%; 78%; 67%; 66%; 69%. Q1 & Q2; 83%; 50%; 67%; 77%; 44%; 78%; 61%; 50%; 64%. CG4 Average performance on group meeting items # 18, 19, 20, 21, 22, 23, 26, 27, 28; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; CGV I; Total. Q1; ND; ND; 44%; ND; ND; 67%; ND; ND; ND; 56%. Q2; 67%; 22%; 56%; 78%; 44%; 67%; 78%; 44%; 44%; 56%. Q1 & Q2; 67%; 22%; 50%; 78%; 44%; 67%; 78%; 44%; 44%; 55%. CG5 Average performance on group meeting items # 18, 19, 20, 21, 22, 23, 26, 27, 28; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; CGV I; Total. Q1; ND; 89%; ND; ND; 89%; ND; ND; ND; ND; 89%. Q2; 67%; 44%; 56%; 67%; 44%; 67%; 78%; 44%; 44%; 57%. Q1 & Q2; 67%; 67%; 56%; 67%; 67%; 67%; 78%; 44%; 44%; 62%. |
| Delivery | - Are the CGVs completing the most important aspects of the home visits including inquiry about health changes, reviewing the lesson materials, overcoming barriers, scheduling follow up visits? | Average QIVC score across CGVs on check list items: 15, 16, 17, 18, 19, 20 across CGVs |  | Average performance on home visit items # 15, 16, 17, 18, 19, 20 – All CGVs; %. Q1; 70%. Q2; 48%. Q1 & Q2; 59%. |
|  |  | Average QIVC score across CGVs on check list items: 15, 16, 17, 18, 19, 20 for each CGV |  | CG1 Average performance on home visit items # 15, 16, 17, 18, 19, 20; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; CGV I; CGV J; Total. Q1; ND; ND; 83%; ND; 83%; ND; ND; ND; 83%; ND; 83%. Q2; 33%; 33%; 33%; 67%; 67%; 17%; 33%; 33%; 50%; 33%; 41%. Q1 & Q2; 33%; 33%; 58%; 67%; 75%; 17%; 33%; 33%; 67%; 33%; 46%. CG2 Average performance on home visit items # 15, 16, 17, 18, 19, 20; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; Total. Q1; ND; ND; ND; ND; 100%; ND; ND; 100%. Q2; 50%; 50%; 50%; 50%; 33%; 50%; 50%; 48%. Q1 & Q2; 50%; 50%; 50%; 50%; 67%; 50%; 50%; 52%. CG3 Average performance on home visit items # 15, 16, 17, 18, 19, 20; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; Total. Q1; 17%; 17%; ND; ND; ND; 33%; ND; ND; 22%. Q2; 67%; 83%; 33%; 50%; 33%; 67%; 83%; 58%; 59%. Q1 & Q2; 42%; 50%; 33%; 50%; 33%; 50%; 83%; 58%; 50%. CG4 Average performance on home visit items # 15, 16, 17, 18, 19, 20; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; CGV I; Total. Q1; ND; ND; ND; ND; ND; ND; ND; ND; ND; ND. Q2; 50%; 17%; 50%; 33%; 50%; 67%; 33%; 33%; 67%; 44%. Q1 & Q2; 50%; 17%; 50%; 33%; 50%; 67%; 33%; 33%; 67%; 44%. CG5 Average performance on home visit items # 15, 16, 17, 18, 19, 20; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; CGV I; Total. Q1; ND; 67%; ND; ND; 83%; ND; ND; ND; ND; 75%. Q2; 83%; 33%; 50%; 67%; 33%; 67%; 50%; 17%; 33%; 48%. Q1 & Q2; 83%; 50%; 50%; 67%; 58%; 67%; 50%; 17%; 33%; 53%. |
| Delivery | - Are CGVs exhibiting mastery of the lesson material? Are CGVs delivering educational content accurately and completely? | Average QIVC scores across all CGVs for check list items #35, 36, and 37 |  | Average performance on group meeting items # 35, 36, 37 – All CGVs; %. Q1; 77%. Q2; 100%. Q1 & Q2; 88%. |
|  |  | Average QIVC scores across all CGVs for check list items #35, 36, and 37 |  | CG1 Average performance on group meeting items # 35, 36, 37; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; CGV I; CGV J; Total. Q1; 67%; ND; ND; ND; ND; 0%; ND; 67%; ND; ND; 33%. Q2; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%. Q1 & Q2; 83%; 100%; 100%; 100%; 100%; 50%; 100%; 83%; 100%; 100%; 93%. CG2 Average performance on group meeting items # 35, 36, 37; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; Total. Q1; 100%; 100%; 100%; ND; 100%; ND; ND; 100%. Q2; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%. Q1 & Q2; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%. CG3 Average performance on group meeting items # 35, 36, 37; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; Total. Q1; 100%; 100%; ND; 100%; 100%; ND; 100%; 100%; 100%. Q2; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%. Q1 & Q2; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%. CG4 Average performance on group meeting items # 35, 36, 37; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; CGV I; Total. Q1; ND; ND; 100%; ND; ND; 0%; ND; ND; ND; 50%. Q2; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%. Q1 & Q2; 100%; 100%; 100%; 100%; 100%; 50%; 100%; 100%; 100%; 94%. CG5 Average performance on group meeting items # 35, 36, 37; CGV A; CGV B; CVG C; CGV D; CGV E; CGV F; CGV G; CGV H; CGV I; Total. Q1; ND; 100%; ND; ND; 100%; ND; ND; ND; ND; 100%. Q2; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%. Q1 & Q2; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%; 100%. |